## Description
Document Name | Development Workflow Best Practices
Version No. | V.1
Release Date | 04th Dec 2012
Version No. | Authored / Modified by | Reviewed by, Date | Approved by, Date | Date Remark / Change History
V1.0 | Yogesh Gaikwad |  |  | Generic FET development workflow as per the project execution cycle updated.

## WorkFlow_BestPractice
Workflow - Best Practices
Steps | Description
New Task
1 | Check all PSDs are with you
2 | Verify Wireframes and PSDs
3 | Get questions answered by POCs
4 | Estimate for the task
5 | Share it with the client and finalize on priorities
6 | Start working on tasks based on priorities (HTML/CSS, JS)
On Markup Completion
7 | Check for standard and guidelines followed and Checklist for UI
8 | Integrate FTLs
9 | Verify pages on Browswer/Tablet/Mobile
10 | Update SPIRA with comments and % complete
11 | Upate DSR with comments as soon as task is complete
12 | Check-in DSR
13 | Inform all team members that DSR is updated
On Task Completion
14 | Check-in code
15 | Raise a flag to client if task is complete
16 | Assign it to client for review
After getting Review Comments, Repeat from step 2 (Ignore steps, if not applicable)
Defects
1 | Check SPIRA on daily basis for assigned tasks
2 | Verify, if defect is valid
3 | Talk to QA team if unable to reproduce
For invalid Defects
4 | Provide reference of Wireframe/Comps/Keylines/eMail - why it is invalid
5 | Add comments to SPIRA ticket and assign back to Assigner
For Valid Defects
6 | Pull questions and get it answered by POCs, if any
7 | Analyse & Estimate for the task
8 | Share it with the client and finalize on priorities
9 | Start working on tasks based on priorities
10 | Check for impact of that fix on other modules / pages / sections
11 | Verify fix on specified resolution or across the mandetory dimensions
On Successful Fix
12 | Check-in code
13 | Update SPIRA Incident with comments and files to push live (URL)
14 | Assign Incident to Sean Dunlop
15 | In exceptional cases assign It back to respective assignee
16 | Keep track of defects assigned to you till the time it gets closed
Page Reviews
1 | Crosscheck PSDs and Keylines
2 | Raise query in case of any discrepancy - For the client
3 | First check - PSDs and developed Markups
4 | Second check - Keylines and developed markups
5 | Check pages on Browsers, Tablet, Mobile
6 | For Browser test - Resize your browser manualy
7 | Create a list of findings
8 | Share the list of findings with Lead / Respective Developer
For Developer
9 | Set priority and resolve issue
10 | After fix, ask reviewer to verify the fix
11 | Check-in code on successful fix
After fixes - For Reviewer
12 | Verify whether findings are resolved on mentioned dimension
13 | Valid fix - Green Signal
14 | Invalid fix - return back to developer
Code Reviews by Peer
For Developer
1 | On page completion raise a flag and share code with your peer
2 | Check for validity of feedback shared
3 | Invalid feedback - educate your peer
4 | If valid - Implement the feedback
For Reviewer
1 | Check for standard and guidelines followed and Checklist for UI
2 | Make sure HTML code is optimized
3 | Make sure CSS code is optimized
4 | Make sure JS code is optimized
5 | Unnecessary HTML objects should be avoided
6 | Duplicate code should be removed
7 | Generic classes should be reused
Code Reviews by Lead
For Reviewer
1 | Check for standard and guidelines followed and Checklist for UI
2 | Make sure HTML code is optimized
3 | Make sure CSS code is optimized
4 | Make sure JS code is optimized
5 | Unnecessary HTML objects should be avoided
6 | Duplicate code should be removed
7 | Generic classes should be reused instead of creating a new
8 | Educate team members wherever applicable